## Compliance
No | Category | Requirement | Priority | SYS-SR Status | Allocation | Verdict | Assessment (as-built, with evidence) | Derived SWRs | Model Verification
SYS-SR-001 | Physical | The rover platform shall have a total mass not exceeding 60 kg, including batteries and excluding payload. | Must | Draft | HW | Not SW | Mass is a hardware property. The URDF carries the CAD assembly mass, 57.27 kg (SolidWorks re-export 2026-10-07, batteries included; SWR-DESC-012). The xlsx Mass Properties sheet still holds the 2026-09-25 snapshot (54.35 kg). Not weighed. | SWR-DESC-012
SYS-SR-002 | Drive | The rover platform shall control 4 wheel drive joints in velocity mode using encoder feedback, at a control rate of at least 50 Hz. | Must | Draft | SW+HW | Partial | Velocity mode on 4 joints with PIDs at 100 Hz and diff_drive at 50 Hz (Compliant), but the DCC1000 encoder feedback refreshes at 10 Hz (100 ms) (rover_controller/README.md:57-58), so feedback is below 50 Hz. Model test tSkidSteerKinematics/testEncoderFeedbackRate fails (KnownDeviation). | SWR-BRG-003, SWR-CTL-001, SWR-CTL-002, SWR-CTL-003, SWR-CTL-004, SWR-CTL-018, SWR-DESC-005, SWR-DESC-006, SWR-DESC-008, SWR-HWI-001, SWR-HWI-002 | tSkidSteerKinematics/testControlRates: PASS; tSkidSteerKinematics/testEncoderFeedbackRate: FAIL (known deviation)
SYS-SR-003 | Drive | The rover platform shall implement skid-steer (differential-drive) kinematics that convert commanded body linear and angular velocity into wheel velocities, and shall publish wheel odometry. | Must | Draft | SW | Partial | Skid-steer via diff_drive with 2 wheels/side and wheel_separation_multiplier 1.659; odometry on odometry/wheels. Kinematic model tests pass; the 5 % field accuracy is not measured and the radius multipliers are uncalibrated (SWR-CTL-007). | SWR-BRG-007, SWR-CTL-002, SWR-CTL-005, SWR-CTL-006, SWR-CTL-007, SWR-CTL-012, SWR-DESC-004, SWR-LOC-001, SWR-LOC-002, SWR-LOC-003, SWR-LOC-004, SWR-LOC-005, SWR-LOC-016 | tSkidSteerKinematics/testStraightOdometryError: PASS; tSkidSteerKinematics/testRotationRoundTrip: PASS
SYS-SR-004 | Performance | The rover platform shall limit linear velocity to a maximum of 1.0 m/s and angular velocity to a maximum of 1.7 rad/s, for commands from any source. | Must | Draft | SW | Compliant | diff_drive limits 0.95 m/s / 1.5 rad/s apply after arbitration, so to every source; model test passes. CRSF node defaults (2.0 / 5.0) exceed the limit but the shipped YAML does not (SWR-CRSF-008). Open Questions answer '1.7 m/s2' read as 1.7 rad/s. | SWR-CRSF-005, SWR-CRSF-007, SWR-CRSF-008, SWR-CTL-008, SWR-CTL-011, SWR-DESC-005 | tCommandArbitration/testSpeedLimitAllSources: PASS; tSkidSteerKinematics/testRimSpeedWithinJointLimit: PASS
SYS-SR-005 | Command | The rover platform shall accept velocity commands from 4 sources ([TBD] e.g. joystick teleoperation, remote/web UI, navigation stack, autonomy/docking) and shall execute only the highest-priority active source. | Must | Draft | SW | Compliant | The 4 sources and their order are fixed in rover_twist_mux.yaml: ELRS (110) > Foxglove joystick (100) > Driver UI (8) > Nav 2 (5). This resolves the SYS-SR [TBD]. Model test passes. | SWR-CRSF-001, SWR-CRSF-002, SWR-CRSF-003, SWR-CRSF-005, SWR-CRSF-022, SWR-CTL-020, SWR-MUX-001, SWR-MUX-002, SWR-MUX-016, SWR-TRN-006, SWR-TRN-008, SWR-TRN-023 | tCommandArbitration/testPriorityOrder: PASS
SYS-SR-006 | Safety | The rover platform shall have at least [TBD] hardware emergency stop button(s) that, when pressed, remove drive power independently of software (stop category 0 or 1 per IEC 60204-1, ISO 13850). | Must | Draft | HW+SW | Partial | One hardware button (Open Questions) sets the PLC latch and opens the contactor independently of software; software only monitors it. The PLC program is outside rover_ros, stop category and SYS-SR-014 distance are TBD. | SWR-CRSF-018, SWR-DESC-007, SWR-HWI-012, SWR-HWI-019, SWR-MUX-004, SWR-MUX-007, SWR-MUX-009, SWR-MUX-010, SWR-TRN-015, SWR-TRN-016, SWR-TRN-017 | tCommandArbitration/testMotionLockMasksAllSources: PASS; tEStopLatch/testHwButtonRemovesDrivePower: PASS; tEStopLatch/testCpuWatchdogLossLatches: PASS
SYS-SR-007 | Safety | The rover platform shall provide a software emergency stop, triggerable through the ROS interface, that commands zero velocity to all drive joints within 100 ms. | Must | Draft | SW | Not Met | write() only sees the SW E-stop after the 10 Hz IO poll reads it back from the PLC. Model: <= 90 ms with an ideal link, 240 ms worst case behind one in-flight Modbus transaction (150 ms timeout). Service/Zenoh latency not included. | SWR-BRG-006, SWR-CRSF-012, SWR-CRSF-014, SWR-HWI-005, SWR-HWI-006, SWR-HWI-007, SWR-HWI-018, SWR-MSG-006, SWR-MUX-004, SWR-MUX-005, SWR-MUX-007, SWR-MUX-008, SWR-MUX-009, SWR-MUX-010, SWR-MUX-019, SWR-SAF-001, SWR-SAF-002, SWR-SAF-005, SWR-TRN-015, SWR-TRN-018, SWR-TRN-020 | tEStopLatch/testSwEStopZeroCommandIdealLink: PASS; tEStopLatch/testSwEStopZeroCommandWorstCaseLink: FAIL (known deviation)
SYS-SR-008 | Safety | After any emergency stop (hardware or software), the rover platform shall remain stopped until an operator performs an explicit reset; releasing the E-stop alone shall not resume motion. | Must | Draft | HW+SW | Compliant | Set-dominant PLC latch held until an explicit latch reset; releasing the button or the SW E-stop does not resume motion. Model tests pass. Deviation vs the internal SAFETY_CHAIN.md: the latch reset has no zero-velocity check (SWR-HWI-010). | SWR-BRG-006, SWR-CRSF-012, SWR-CRSF-013, SWR-CRSF-022, SWR-DESC-009, SWR-HWI-004, SWR-HWI-005, SWR-HWI-008, SWR-HWI-009, SWR-HWI-010, SWR-HWI-011, SWR-HWI-018, SWR-HWI-024, SWR-MUX-004, SWR-MUX-010, SWR-SAF-019, SWR-TRN-016 | tEStopLatch/testStartupLatched: PASS; tEStopLatch/testLatchHoldsAfterButtonRelease: PASS; tEStopLatch/testSetDominantLatch: PASS; tEStopLatch/testSwEStopNeedsLatchReset: PASS; tPlatformModeManager/testEStopHasPriorityAndNeedsClear: PASS
SYS-SR-009 | HMI | The rover platform shall indicate its current system state on the LED panels according to a defined state-to-LED mapping (colour and pattern for each state in SYS-SR-010). | Should | Draft | SW | Partial | LED panels show E_STOP only for the hardware button; SW E-stop and a held latch show READY; no Boot, Autonomous, Fault or Idle mapping and no documented mapping table (SWR-SAF-014/022, SWR-LED-020/021). | SWR-LED-001, SWR-LED-002, SWR-LED-003, SWR-LED-004, SWR-LED-005, SWR-LED-006, SWR-LED-009, SWR-LED-010, SWR-LED-011, SWR-LED-012, SWR-LED-013, SWR-LED-014, SWR-LED-015, SWR-LED-019, SWR-LED-020, SWR-LED-021, SWR-MSG-010, SWR-SAF-013, SWR-SAF-014, SWR-SAF-015, SWR-SAF-016, SWR-SAF-022, SWR-TRN-009 | tPlatformModeManager/testLedMapping: PASS; tPlatformModeManager/testLedDefinedForEveryState: FAIL (known deviation)
SYS-SR-010 | States | The rover platform shall implement a defined system state machine with at least these states: Boot, Idle, Teleoperation, Autonomous, Emergency Stop, Fault, Low Battery. | Must | Proposed | SW | Gap | No system state machine exists. Proposed: PlatformModeManager (behaviour model) implemented in rover_safety (SWR-SAF-018..021) with a system-state message (SWR-MSG-011) and the active mux source (SWR-MUX-020). | SWR-BRG-006, SWR-LED-010, SWR-LED-020, SWR-LED-021, SWR-MSG-010, SWR-MSG-011, SWR-MUX-020, SWR-SAF-018, SWR-SAF-019, SWR-SAF-020, SWR-SAF-021, SWR-SAF-022 | tPlatformModeManager/testEveryStateReachable: PASS; tPlatformModeManager/testTeleopAutonomousFollowActiveSource: PASS; tPlatformModeManager/testEStopHasPriorityAndNeedsClear: PASS; tPlatformModeManager/testFaultNeedsReset: PASS; tPlatformModeManager/testNoMotionOutsideOperationalStates: PASS
SYS-SR-011 | Safety | The rover platform shall bring itself to a stop if no valid velocity command is received from the active source within 500 ms. | Must | Proposed | SW | Partial | twist_mux timeouts and diff_drive cmd_vel_timeout 0.5 s stop the rover, but the timeout is checked with '>' at 50 Hz, so deceleration starts up to 520 ms after the last command (model test, KnownDeviation). DCC1000 hardware failsafe 500 ms as back-up. | SWR-CRSF-004, SWR-CRSF-009, SWR-CTL-010, SWR-DESC-008, SWR-HWI-020, SWR-MUX-003, SWR-MUX-014, SWR-MUX-015 | tCommandArbitration/testCommandWatchdog: FAIL (known deviation)
SYS-SR-012 | Safety | The rover platform shall stop if communication with the operator station is lost for more than [TBD] s. | Must | Proposed | SW | Blocked (TBD) | RC link loss: zero burst then silence after 200 ms (up to 1 s via link stats); Driver UI freshness filter; stale safety input locks motion after 1 s. No stop on operator-station loss for the web link; timeout value TBD. | SWR-CRSF-009, SWR-CRSF-010, SWR-CRSF-011, SWR-MSG-009, SWR-MUX-003, SWR-MUX-014 | tCommandArbitration/testStaleSafetyLocks: PASS
SYS-SR-013 | Performance | The rover platform shall limit linear acceleration and deceleration to [TBD] m/s^2 and angular acceleration to [TBD] rad/s^2. | Should | Proposed | SW | Blocked (TBD) | diff_drive limits 2.7 m/s^2 and 3.74 rad/s^2 are enforced (model test passes); the SYS-SR values are TBD. | SWR-CTL-009 | tCommandArbitration/testAccelerationLimit: PASS
SYS-SR-014 | Safety | The rover platform shall stop from 1.0 m/s within [TBD] m on flat, dry, hard ground when any emergency stop is triggered. | Must | Proposed | HW+SW | Blocked (TBD) | Stopping distance depends on the PLC/contactor stop (category TBD) and the drive train. For software-commanded stops the 2.7 m/s^2 limit gives 0.95^2/(2*2.7) = 0.17 m plus latency. Limit TBD. No SWR derived. | SWR-CTL-009, SWR-HWI-003, SWR-HWI-005
SYS-SR-015 | Power | The rover platform shall operate continuously for at least [TBD] h on a full battery charge under a [TBD] duty cycle. | Must | Proposed | HW | Not SW | Endurance is set by the battery (design_capacity 40 Ah) and the duty cycle; values TBD. | SWR-DESC-016
SYS-SR-016 | Power | The rover platform shall publish battery voltage, current and state of charge at 1 Hz or faster. | Must | Proposed | SW | Not Met | battery_status is published once per BMS UDP packet with a 10 s watchdog, so >= 1 Hz is not guaranteed; header not stamped; 5 % accuracy not measured (SWR-BAT-003/012/013/014). | SWR-BAT-001, SWR-BAT-002, SWR-BAT-003, SWR-BAT-004, SWR-BAT-008, SWR-BAT-012, SWR-BAT-013, SWR-BAT-014, SWR-SAF-001, SWR-TRN-006, SWR-TRN-007, SWR-TRN-008
SYS-SR-017 | Power | The rover platform shall enter the Low Battery state at [TBD]% state of charge and shall perform a safe stop at [TBD]% state of charge. | Must | Proposed | SW | Gap | Thresholds TBD. Today: LED warnings at 40 % / 10 % only; the BMS DEAD alarm trips the E-stop via rover_safety. No Low Battery state or SOC-based safe stop (SWR-SAF-020, proposed model). | SWR-BAT-005, SWR-BAT-008, SWR-SAF-002, SWR-SAF-005, SWR-SAF-006, SWR-SAF-020 | tPlatformModeManager/testLowBatteryWarningAndSafeStop: PASS
SYS-SR-018 | Power | The rover platform shall support battery charging via [TBD: external connector / docking station] without removing the battery. | Should | Proposed | HW | Not SW | Charging method TBD (hardware). Software only reports charging_status (SWR-BAT-006/007). | SWR-BAT-006, SWR-BAT-007
SYS-SR-019 | Sensors | The rover platform shall include an IMU that publishes orientation, angular velocity and linear acceleration at 100 Hz or faster. | Should | Proposed | SW | Not Met | The Phidget IMU samples at 125 Hz but imu_sensor_broadcaster publishes imu/data at 50 Hz (wheel_01_controller.yaml:150); the simulated IMU is 50 Hz too. Model test fails (KnownDeviation). | SWR-CTL-014, SWR-CTL-015, SWR-DESC-010, SWR-DESC-015, SWR-HWI-026, SWR-LOC-004 | tSkidSteerKinematics/testImuPublishRate: FAIL (known deviation)
SYS-SR-020 | Software | The rover platform software shall be based on ROS 2 [TBD distribution] and shall use ros2_control for the drive hardware interface. | Must | Proposed | SW | Compliant | ROS 2 Lyrical with rmw_zenoh_cpp, ros2_control hardware interface RoverA1System. Resolves the SYS-SR [TBD distribution]. | SWR-BRG-003, SWR-BRG-009, SWR-BRG-010, SWR-DESC-001, SWR-DESC-006, SWR-HWI-001, SWR-MSG-012, SWR-TRN-022
SYS-SR-021 | Software | The rover platform shall follow ROS REP-103 (units and conventions) and REP-105 (coordinate frames: map, odom, base_link). | Must | Proposed | SW | Compliant | REP-103 axes and REP-105 frames (odom -> base_footprint from the EKF, base_link, sensor frames). map -> odom comes from the orchestrator (SLAM/AMCL) or the optional GPS EKF, outside the platform by default. | SWR-BAT-004, SWR-BAT-013, SWR-BRG-007, SWR-CTL-006, SWR-CTL-013, SWR-DESC-002, SWR-DESC-003, SWR-DESC-004, SWR-DESC-011, SWR-DESC-013, SWR-GPSH-001, SWR-GPSH-002, SWR-GPSH-003, SWR-GPSH-004, SWR-GPSH-005, SWR-GPSH-006, SWR-GPSH-007, SWR-GPSH-008, SWR-HWI-002, SWR-LOC-005, SWR-LOC-006, SWR-LOC-009, SWR-LOC-010, SWR-LOC-011, SWR-LOC-012, SWR-LOC-016
SYS-SR-022 | Software | The rover platform shall publish diagnostic status for drive motors, battery, E-stop circuit and sensors on /diagnostics at 1 Hz or faster. | Should | Proposed | SW | Partial | Every node publishes diagnostics at 1 Hz and the aggregator at 1.0 Hz (no margin). Gaps: no expected/timeout entries in the aggregator, no IMU diagnostic, the PLC link diagnostic never goes ERROR, no transport diagnostics. | SWR-BAT-005, SWR-BAT-008, SWR-BAT-010, SWR-BRG-004, SWR-CRSF-021, SWR-DIAG-005, SWR-DIAG-006, SWR-DIAG-007, SWR-DIAG-009, SWR-DIAG-010, SWR-DIAG-011, SWR-DIAG-012, SWR-GPSH-011, SWR-GPSH-012, SWR-HWI-015, SWR-HWI-017, SWR-HWI-021, SWR-HWI-022, SWR-HWI-023, SWR-HWI-024, SWR-HWI-027, SWR-LED-017, SWR-LED-018, SWR-LOC-008, SWR-MSG-002, SWR-MSG-004, SWR-MSG-008, SWR-MUX-013, SWR-MUX-018, SWR-SAF-009, SWR-SAF-012, SWR-SAF-017, SWR-SAF-021, SWR-TRN-008, SWR-TRN-021
SYS-SR-023 | Safety | The rover platform shall publish the state of the hardware and software emergency stops on a ROS topic within 100 ms of a change. | Must | Proposed | SW | Not Met | E-stop state reaches hardware_interface/safety_status through the 10 Hz IO poll and the 20 Hz publisher: up to 130 ms in the model (KnownDeviation), more with Modbus delays. | SWR-DESC-007, SWR-HWI-013, SWR-HWI-014, SWR-HWI-015, SWR-HWI-016, SWR-HWI-017, SWR-MSG-001, SWR-MSG-002, SWR-MSG-003, SWR-MSG-004, SWR-MSG-005, SWR-MUX-005, SWR-MUX-006, SWR-MUX-008, SWR-TRN-015, SWR-TRN-018, SWR-TRN-019, SWR-TRN-020 | tEStopLatch/testEStopStatePublishLatency: FAIL (known deviation)
SYS-SR-024 | Software | The rover platform shall start all platform software automatically on power-up and reach the Idle state within [TBD] s. | Should | Proposed | SW+Deployment | Partial | Auto-start on power-up is done by rover_docker (outside rover_ros) and rover_bringup's staged start; there is no Idle state and the time is TBD. | SWR-BAT-011, SWR-BRG-001, SWR-BRG-005, SWR-BRG-011, SWR-BRG-015, SWR-CRSF-015, SWR-CTL-017, SWR-HWI-004, SWR-HWI-011, SWR-LED-015, SWR-LED-019, SWR-SAF-010, SWR-SAF-019, SWR-TRN-005, SWR-TRN-017
SYS-SR-025 | Communication | The rover platform shall provide a wireless link to the operator station with a line-of-sight range of at least [TBD] m and a round-trip latency of at most [TBD] ms. | Must | Proposed | HW+SW | Blocked (TBD) | Links: ExpressLRS RC (receiver UART on the RUTX11 router, forwarded to the platform over UDP 10111) and LAN/Wi-Fi websocket (foxglove_bridge 8765, rosbridge 9090). Range and latency TBD and depend on the radio hardware. | SWR-BRG-012, SWR-BRG-013, SWR-BRG-014, SWR-CRSF-010
SYS-SR-026 | Physical | The rover platform shall not exceed [TBD] x [TBD] x [TBD] mm (L x W x H). | Should | Proposed | HW | Not SW | Dimensions. The footprint is 0.923 x 0.802 m (CAD tyre outline + 0.04 m; Nav 2 footprint, outside rover_ros); limit TBD.
SYS-SR-027 | Physical | The rover platform shall carry a payload of at least [TBD] kg while still meeting SYS-SR-004 and SYS-SR-014. | Must | Proposed | HW | Not SW | Payload capacity; TBD.
SYS-SR-028 | Environment | The rover platform shall operate on slopes up to [TBD] degrees on [TBD] terrain types. | Should | Proposed | HW | Not SW | Slope/terrain; TBD. Static sideways tip-over: tyre contact half-track 0.3068 m (URDF) and CoM height 0.215 m above the ground (CAD 2026-10-07 in the URDF frame): atan(0.3068/0.215) = 55.0 deg. The xlsx Mass Properties sheet gives a CoM height of 0.270 m from an older snapshot with a different origin.
SYS-SR-029 | Environment | The rover platform shall operate at ambient temperatures from [TBD] to [TBD] degC and shall meet ingress protection IP[TBD]. | Should | Proposed | HW | Not SW | Temperature range and IP rating; TBD.

## Verdict Legend
Verdict | Meaning
Compliant | The as-built software meets the requirement (by evidence and/or model test).
Partial | Implemented, but part of the requirement is unmet or unverified.
Not Met | The as-built software contradicts the requirement (evidence and/or failing model test).
Gap | Not implemented in rover_ros.
Blocked (TBD) | Cannot be judged until the [TBD] values in the SYS-SR are set.
Not SW | Allocated to hardware, mechanics or the environment; no software requirement derived.

## Findings
SWR | Package | Implementation | Status | Parent SYS-SR | Requirement | Evidence | Comments
SWR-BAT-003 | rover_battery | Partial | As-Built | SYS-SR-016 | The rover_battery shall publish sensor_msgs/BatteryState on rover_battery/battery_status (depth 5, reliable, volatile) once for every valid BMS frame received. | rover_battery/src/infrastructure/ros2_battery_state_publisher.cpp:83; rover_battery/src/infrastructure/ros2_battery_state_publisher.cpp:91-95; rover_battery/src/application/monitor_battery_use_case.cpp:37-43 | Publication is event-driven, so its rate equals the ESP32 packet rate, which is not specified in this package; see SWR-BAT-012 for the SYS-SR-016 >= 1 Hz requirement.
SWR-BAT-012 | rover_battery | Gap | Proposed | SYS-SR-016 | The rover_battery shall publish rover_battery/battery_status at 1 Hz or faster regardless of the BMS packet timing, republishing the latest reading on a fixed-rate timer, and shall enter the watchdog state (SWR-BAT-008) when the latest reading is older than [TBD] s. | rover_battery/src/infrastructure/rover_battery_node.cpp:79-82; rover_battery/src/infrastructure/rover_battery_node.cpp:110-111; rover_battery/config/rover_battery.yaml:13 | The ESP32 send period is not documented in this package; measure it before choosing the staleness limit.
SWR-BAT-013 | rover_battery | Gap | Proposed | SYS-SR-016, SYS-SR-021 | The rover_battery shall set BatteryState.header.stamp to the time the BMS frame was received (or the watchdog fired) and header.frame_id to a battery frame name. | rover_battery/src/infrastructure/battery_msg_conversions.cpp:78-96 | Frame name TBD (URDF has no battery link identified in this review).
SWR-BAT-014 | rover_battery | Partial | Proposed | SYS-SR-016 | The rover_battery shall report pack voltage, current and state of charge within 5 % of a reference meter. | rover_battery/src/domain/battery_classifier.cpp:193-200 | Conversions are implemented and unit-tested; the end-to-end accuracy has never been measured. Test points TBC.
SWR-BAT-015 | rover_battery | Gap | Proposed |  | The rover_battery shall implement rover_battery_node as a managed lifecycle node that creates its subscription, publishers and watchdog timer in configure/activate and is brought to ACTIVE by an autostart parameter. | rover_battery/src/infrastructure/rover_battery_node.cpp:36-40; rover_battery/launch/rover_battery.launch.py:73-81 | The launch passes autostart only to the UDP receiver (launch line 68), not to rover_battery_node.
SWR-BRG-010 | rover_bringup | Partial | As-Built | SYS-SR-020 | The rover_bringup shall run on the ROS 2 distribution fixed in SYS-SR-020 with rmw_zenoh_cpp as the RMW implementation. | README.md:88; rover_scripts/setup_rover_pc.sh:104; rover_bringup/package.xml:34 | SYS-SR-020 distribution is [TBD]; the workspace README uses ROS_DISTRO=lyrical. The RMW is set by the environment (setup script / container), not by rover_bringup itself. Update SYS-SR-020 to 'Lyrical' [TBC].
SWR-BRG-011 | rover_bringup | Gap | Proposed | SYS-SR-024 | The rover_bringup shall be started automatically at power-up and bring the platform to the Idle state within [TBD per SYS-SR-024] s. | rover_bringup/README.md:10-11; rover_bringup/launch/rover_bringup.launch.py:266-288 | Auto-start is provided outside this boundary by the rover_docker container (rovera1-app start.sh). No 'Idle' state is defined or reported anywhere in the bringup, and no start-up time is measured; the only bound is the 20.0 s controllers_ready_timeout fallback. Needs a state-publishing node (SYS-SR-010) and a boot-time test.
SWR-BRG-015 | rover_bringup | Gap | Proposed | SYS-SR-024 | The rover_bringup shall have an automated launch test that verifies the two-stage start order and that all platform nodes are running after start-up. | rover_bringup/CMakeLists.txt:8-12 | The only test is the foxglove whitelist unit test.
SWR-CTL-007 | rover_controller | Partial | Proposed | SYS-SR-003 | The rover_controller shall produce wheel odometry whose travelled-distance error is <= 5 % [TBC per SYS-SR-003] when the rover drives 10 m straight at 0.5 m/s on flat ground. | rover_controller/config/wheel_01_controller.yaml:173-178; rover_controller/rover_controller/wheel_odom_calibration.py:38-47; rover_controller/README.md:83-95 | A calibration tool exists (wheel_odom_calibration, straight mode) but left/right_wheel_radius_multiplier are still 1.0 and no recorded calibration result exists in the package. 5 % is [TBC] in SYS-SR-003.
SWR-CTL-009 | rover_controller | Partial | As-Built | SYS-SR-013, SYS-SR-014 | The rover_controller shall limit rover_drive_controller linear acceleration and deceleration to 2.7 m/s^2 and angular acceleration and deceleration to 3.74 rad/s^2 in both directions. | rover_controller/config/wheel_01_controller.yaml:205-225; rover_controller/README.md:72-81 | SYS-SR-013 limits are [TBD]; compliance cannot be judged until they are set. Jerk limits are NaN (disabled). test_response_analysis.py covers the tool that derives the limits, not the limits themselves.
SWR-CTL-015 | rover_controller | Gap | Proposed | SYS-SR-019 | The rover_controller shall publish imu/data at 100 Hz or faster. | rover_controller/config/wheel_01_controller.yaml:140; rover_controller/config/wheel_01_controller.yaml:148-150 | Setting update_rate 100 would meet SYS-SR-019 at the cost of Zenoh traffic; alternatively the SYS-SR-019 rate could be revised to 50 Hz. Decision needed.
SWR-CRSF-008 | rover_crsf_teleop | Deviation | Proposed | SYS-SR-004 | The rover_crsf_teleop shall declare linear_x_out_min/max and angular_z_out_min/max defaults no larger in magnitude than 1.0 m/s and 1.7 rad/s and shall refuse to configure with values beyond those limits. | rover_crsf_teleop/src/infrastructure/rover_crsf_teleop_node.cpp:153-159; rover_crsf_teleop/src/application/teleop_config_validation.cpp:117-139 | Downstream diff_drive limits (rover_controller) still clip, so this is defence in depth. Other code defaults also differ from the shipped YAML (zero_burst_duration_ms 0 vs 300, rc_channels_expected_hz 50 vs 250, expo 0 vs 0.3/0.5).
SWR-CRSF-014 | rover_crsf_teleop | Gap | Proposed | SYS-SR-007 | The rover_crsf_teleop shall keep requesting hardware_interface/sw_user_e_stop_set while the e_stop_channel switch is low and the request has not been acknowledged with success (service unavailable, pending or refused), instead of dropping the request. | rover_crsf_teleop/src/infrastructure/ros2_trigger_safety_switch.cpp:87-94; rover_crsf_teleop/src/application/teleop_use_case.cpp:178-185 | Outcome (unavailable/refused) is visible on the 'E-Stop requests' diagnostic as WARN today. Must not retry the reset/latch-reset requests the same way (a reset must stay a deliberate edge per SYS-SR-008).
SWR-DESC-012 | rover_description | Deviation | As-Built | SYS-SR-001 | The rover_description shall declare body_link inertial mass 36.9775 kg and each wheel link mass 5.0741 kg (57.2739 kg in total). | rover_description/urdf/rover_a1/base.urdf.xacro:68-79; rover_description/config/wheel_01.yaml:10; rover_description/urdf/common/wheel.urdf.xacro:74-84 | Mass fidelity: 57.27 kg is the SolidWorks assembly mass (ROVER_1000_WATT_VARIANT, re-exported 2026-10-07, batteries included), not a measured value; it does not by itself verify SYS-SR-001. The four DCC1000 motor controllers carry an ASSUMPTION mass (78.8 g each, not weighed). The URDF exporter ignores mass overrides, so body_link mass is the exported 37.2298 kg corrected by -0.2522 kg by hand (base.urdf.xacro comment). Sensors have no inertial links.
SWR-DESC-015 | rover_description | Gap | Proposed | SYS-SR-019 | The rover_description shall configure the simulated IMU update_rate at 100 Hz or faster. | rover_description/urdf/common/imu.urdf.xacro:57 | Simulated IMU is 50 Hz today, matching the 50 Hz imu broadcaster (rover_controller).
SWR-DIAG-012 | rover_diag_manager | Gap | Proposed | SYS-SR-022 | The rover_diag_manager shall configure the diagnostic aggregator so that the drive, battery, E-stop (safety) and sensor (GPS, lidar, IMU) groups report ERROR or STALE when an expected component's diagnostics are missing, rather than silently omitting them. | rover_diag_manager/config/diagnostic_aggregator.yaml:20-57 | No 'expected' / 'contains' entries or timeout are configured in any analyzer, so a missing node's group simply disappears. Proposed fix: add expected status names per group.
SWR-HWI-007 | rover_hardware_interface | Partial | Proposed | SYS-SR-007 | The rover_hardware_interface shall command zero velocity to all four drive joints within 100 ms of a hardware_interface/sw_user_e_stop_set request being received. | rover_hardware_interface/src/rover_safety_controller/rover_safety_controller_e_stop_io.cpp:29-32; rover_hardware_interface/src/rover_safety_controller/rover_safety_controller.cpp:475-514; rover_hardware_interface/src/rover_system/rover_system.cpp:343; rover_hardware_interface/src/rover_system/rover_system.cpp:363-391; rover_description/urdf/rover_a1/rover_a1_macro.urdf.xacro:160; rover_description/urdf/rover_a1/rover_a1_macro.urdf.xacro:178 | Not verified: worst case exceeds 100 ms by analysis (in-flight Modbus transaction up to 150 ms + write + up to 100 ms poll + 10 ms). Candidate fix: latch a local "sw E-Stop requested" flag in EmergencyStop::setEStop() that write() honours on the next cycle, independent of the PLC read-back. The hardware contactor path (PLC latch) is not bounded by this software latency.
SWR-HWI-010 | rover_hardware_interface | Deviation | Proposed | SYS-SR-008 | The rover_hardware_interface shall refuse hardware_interface/sw_e_stop_latch_reset (success=false) while any wheel velocity command exceeds velocity_command_zero_tolerance or any measured wheel velocity exceeds velocity_state_zero_tolerance. | rover_hardware_interface/src/rover_system/rover_system.cpp:674-706; rover_hardware_interface/src/domain/emergency_stop.cpp:99-109; rover_arch/SAFETY_CHAIN.md:211-216 | Deviation between code and SAFETY_CHAIN.md §5. rover_twist_mux motion_lock and diff_drive cmd_vel_timeout (0.5 s) mitigate but do not enforce the invariant at the hardware interface.
SWR-HWI-016 | rover_hardware_interface | Partial | Proposed | SYS-SR-023 | The rover_hardware_interface shall publish a change of the hardware E-Stop button, software E-Stop coil or PLC latch state on hardware_interface/safety_status or hardware_interface/safety_command_echo within 100 ms of the change at the PLC. | rover_description/urdf/rover_a1/rover_a1_macro.urdf.xacro:178; rover_description/urdf/rover_a1/rover_a1_macro.urdf.xacro:190; rover_hardware_interface/src/rover_system/rover_system.cpp:329-341; rover_hardware_interface/src/rover_safety_controller/rover_safety_controller.cpp:475-514 | Not verified. Worst case by analysis ~150 ms plus transaction time, i.e. above 100 ms. Options: poll at 50 ms, or publish the safety topics on each fresh poll rather than on the 20 Hz driver-state tick.
SWR-HWI-017 | rover_hardware_interface | Gap | Proposed | SYS-SR-023, SYS-SR-022 | The rover_hardware_interface shall populate SafetyStatus.latch_cause with the trip source that set the PLC latch (SW user button, SW motor-driver fault, CPU watchdog or HW user button). | rover_hardware_interface/src/system_ros_interface/system_ros_interface.cpp:314-341; rover_msgs/msg/SafetyStatus.msg:35-47; rover_arch/SAFETY_CHAIN.md:222-227 | latch_cause is never assigned in rover_hardware_interface (grep finds no write), so it is always LATCH_CAUSE_UNKNOWN (0). Needs a PLC program change that latches the cause into readable coils.
SWR-HWI-018 | rover_hardware_interface | Deviation | Proposed | SYS-SR-007, SYS-SR-008 | The rover_hardware_interface shall assert the sw_e_stop_motor_driver_fault coil (COIL_3) when a motor-driver fault (latched MOTOR_FAILSAFE_TRIPPED or FAULT_FLAG error) is detected, so that the PLC latch opens the contactor. | rover_hardware_interface/src/domain/emergency_stop.cpp:111-118; rover_hardware_interface/src/rover_safety_controller/rover_safety_controller.cpp:239-244; rover_arch/SAFETY_CHAIN.md:17-21 | triggerMotorDriverFault() is only ever called with false (start-up release); COIL_3 is never asserted at runtime. Driver faults today inhibit motion only through write() zero commands.
SWR-HWI-023 | rover_hardware_interface | Deviation | Proposed | SYS-SR-022 | The rover_hardware_interface shall report the "safety plc link" diagnostic as ERROR when the last successful IO poll is older than 500 ms or when IO polls keep failing, even while both safety threads are running. | rover_hardware_interface/src/domain/safety_link_diagnosis.cpp:20-53; rover_hardware_interface/src/system_ros_interface/system_ros_interface.cpp:288-295; rover_hardware_interface/test/domain/test_safety_link_diagnosis.cpp:159 | evaluateSafetyLinkHealth() only escalates on thread state and contactor faults; the test ErrorCountersAndAgesNeverRaiseTheLevel pins that poll errors and ages never raise the level, so /diagnostics can read OK while SafetyStatus.link_healthy is false.
SWR-HWI-027 | rover_hardware_interface | Gap | Proposed | SYS-SR-022 | The rover_hardware_interface shall publish an IMU diagnostic status on diagnostics at >= 1 Hz that reports ERROR while the Phidgets Spatial is detached or delivers no valid samples. | rover_hardware_interface/src/rover_sensors/phidget_imu_sensor.cpp:170-200 | No diagnostics code in phidget_imu_sensor.cpp / .hpp (grep for "diagnos" finds none).
SWR-LED-010 | rover_led | Partial | As-Built | SYS-SR-009, SYS-SR-010 | The rover_led shall provide a catalog animation for each of the SYS-SR-010 states Emergency Stop (E_STOP, id 0, STATE layer), Idle (READY, id 1, STATE), Teleoperation (MANUAL_ACTION, id 4, STATE), Autonomous (AUTONOMOUS_READY id 11 and AUTONOMOUS_ACTION id 12, STATE), Fault (ERROR, id 2, ERROR layer) and Low Battery (LOW_BATTERY id 5 and CRITICAL_BATTERY id 6, INFO layer). | rover_led/config/rover_a1_animations.yaml:32-34; rover_led/config/rover_a1_animations.yaml:47-49; rover_led/config/rover_a1_animations.yaml:62-64; rover_led/config/rover_a1_animations.yaml:84-86; rover_led/config/rover_a1_animations.yaml:99-101; rover_led/config/rover_a1_animations.yaml:124-126; rover_led/config/rover_a1_animations.yaml:225-227; rover_led/config/rover_a1_animations.yaml:240-242 | Partial: no Boot animation exists (see SWR-LED-020). The mapping state -> id is an interpretation: the system has no explicit Idle state, READY is the closest. Which animation is shown is decided by rover_safety (behavior_trees/rover_led_safety.xml), whose StateAnimationSubtree only selects READY, MANUAL_ACTION and E_STOP; nothing in rover_safety requests AUTONOMOUS_READY/AUTONOMOUS_ACTION (outside this package, flagged for the rover_safety SWRS).
SWR-LED-020 | rover_led | Gap | Proposed | SYS-SR-009, SYS-SR-010 | The rover_led shall provide a catalog animation (and a matching rover_msgs/LedAnimation constant) for the SYS-SR-010 Boot state, shown on both panels from the moment the LED driver becomes Active until a client selects another state animation. | rover_msgs/msg/LedAnimation.msg:1-18; rover_led/config/rover_a1_animations.yaml:31-325; rover_led/src/infrastructure/led_driver_node.cpp:166-168 | No BOOT id exists in LedAnimation.msg or the catalog, and the driver clears the LEDs on activation. Colour/pattern TBD (depends on the SYS-SR-009 mapping).
SWR-LED-021 | rover_led | Partial | Proposed | SYS-SR-009, SYS-SR-010 | The rover_led shall document, in the package, the state-to-LED mapping required by SYS-SR-009: for each SYS-SR-010 state the animation id, layer, colour and pattern (steady/blinking/moving, period) shown on the front and rear panels. | rover_led/README.md:76-157; rover_led/config/rover_a1_animations.yaml:36-45 | The README documents the layers and animation types but not the colour/pattern per state; the images (e.g. animations/rover_a1/estop_front.png) define them implicitly.
SWR-LOC-015 | rover_localization | Deviation | Proposed |  | The rover_localization shall ship a valid configuration file for every value accepted by the localization_mode argument, including enu. | rover_localization/launch/rover_localization.launch.py:49-59; rover_localization/launch/rover_localization.launch.py:107-111; rover_localization/README.md:113-114 | Only rel_localization.yaml and rel_localization_with_gps.yaml exist in config/; localization_mode:=enu resolves to enu_localization*.yaml, which is missing.
SWR-LOC-016 | rover_localization | Gap | Proposed | SYS-SR-003, SYS-SR-021 | The rover_localization shall have an automated test that verifies the EKF publishes odom at >= 47.5 Hz and the odom -> base_footprint transform from recorded or simulated wheel-odometry and IMU input. | rover_localization/CMakeLists.txt:1-8 | CMakeLists.txt only installs config and launch; no BUILD_TESTING block and no test/ directory.
SWR-MSG-004 | rover_msgs | Partial | As-Built | SYS-SR-023, SYS-SR-022 | The rover_msgs shall define the SafetyStatus latch_cause constants LATCH_CAUSE_UNKNOWN = 0, LATCH_CAUSE_SW_USER_BUTTON = 1, LATCH_CAUSE_SW_MOTOR_DRIVER_FAULT = 2, LATCH_CAUSE_CPU_WATCHDOG = 3 and LATCH_CAUSE_HW_USER_BUTTON = 4. | rover_msgs/msg/SafetyStatus.msg:35-47 | Contract defined, but the publisher never sets the field, so it is always LATCH_CAUSE_UNKNOWN (see rover_hardware_interface SWRS, latch_cause requirement).
SWR-MSG-010 | rover_msgs | Partial | Proposed | SYS-SR-009, SYS-SR-010 | The rover_msgs shall define rover_msgs/LedAnimation animation ids covering every SYS-SR-010 system state, including a Boot state. | rover_msgs/msg/LedAnimation.msg:1-21 | Existing ids plausibly cover Idle (READY), Teleoperation (MANUAL_ACTION), Autonomous (AUTONOMOUS_READY / AUTONOMOUS_ACTION), Emergency Stop (E_STOP), Fault (ERROR) and Low Battery (LOW_BATTERY); there is no Boot id. The state-to-id mapping is an interpretation (TBC) and is not documented in rover_msgs. rover_safety/test/unit/test_led_animation_policy.cpp covers the current policy in rover_safety.
SWR-MSG-011 | rover_msgs | Gap | Proposed | SYS-SR-010 | The rover_msgs shall define a system-state message whose state constants enumerate at least Boot, Idle, Teleoperation, Autonomous, Emergency Stop, Fault and Low Battery. | rover_msgs/msg/SystemStatus.msg:1-7; rover_msgs/CMakeLists.txt:15-63 | SystemStatus carries only CPU / RAM / disk telemetry. MissionState and LocalizationState cover sub-states of navigation only.
SWR-SAF-006 | rover_safety | Deviation | Proposed | SYS-SR-017 | The rover_safety shall, in rover_safety_node, evaluate and act on the battery verdict as soon as a battery reading and the software E-Stop state are available, independently of whether system_status (CPU temperature) has been received. | rover_safety/src/safety_node.cpp:274-288; rover_safety/src/safety_node.cpp:304-308 | cpu_temp is only read into diagnostics; no tree node uses it. The 'Safety behavior tree' diagnostic does show the not-ready condition.
SWR-SAF-012 | rover_safety | Gap | Proposed | SYS-SR-022 | The rover_safety shall, in rover_safety_node, evaluate motor-driver temperature from hardware_interface/rover_driver_state and trip the software E-Stop above a driver temperature limit of [TBD] degC. | rover_safety/src/safety_node.cpp:247-257; rover_safety/README.md:263-265 | Declared but unused parameters: cpu.temp.*, driver.temp.* (fan_on/fan_off/window_len), battery.temp.window_len, fan_turn_off_timeout (safety_parameters.yaml:18-79). No fan hardware control exists; remove the fan parameters or implement fan control. The limit value has no source yet (TBD).
SWR-SAF-014 | rover_safety | Deviation | As-Built | SYS-SR-009 | The rover_safety shall, in rover_led_safety_node, select the state animation E_STOP while SafetyStatus.hw_e_stop_user_button is true, otherwise MANUAL_ACTION while joy button 4 (dead-man) is held, otherwise READY. | rover_safety/src/domain/led_animation_policy.cpp:29-35; rover_safety/src/led_safety_node.cpp:233-248; rover_safety/include/rover_safety/led_safety_node.hpp:99 | Deviation from SYS-SR-009/SYS-SR-010: only the hardware button shows E_STOP. A software E-Stop, a motor-driver-fault stop or a held latch after the button was released shows READY although the rover cannot move. Superseded by SWR-SAF-022.
SWR-SAF-018 | rover_safety | Gap | Proposed | SYS-SR-010 | The rover_safety shall provide a platform mode manager that maintains exactly one current system state out of Boot, Idle, Teleoperation, Autonomous, Emergency Stop, Fault and Low Battery, and publishes it on a ROS topic with reliable, transient-local QoS (depth 1) on every change. | rover_safety/src/safety_node.cpp:290-317; rover_safety/src/domain/led_animation_policy.cpp:29-35 | Allocation to rover_safety is a proposal (it already aggregates battery and safety inputs and drives the LEDs). QoS follows .claude/rules/ros2_communication.md (state = reliable, transient-local, depth 1). Message type to be defined in rover_msgs.
SWR-SAF-019 | rover_safety | Gap | Proposed | SYS-SR-010, SYS-SR-008, SYS-SR-024 | The rover_safety shall, in its platform mode manager, implement these transitions: Boot -> Idle once all platform nodes are active and the first fresh SafetyStatus has been received; Idle <-> Teleoperation / Autonomous according to the twist_mux input currently selected (teleop inputs vs nav); any state -> Emergency Stop while any stop condition of SafetyStatus/SafetyCommandEcho is active (HW button, SW button, motor-driver fault, latch); Emergency Stop -> Idle only after the latch has been reset; Boot -> Idle within [TBD per SYS-SR-024] s of power-up. | rover_safety/src/safety_node.cpp:259-263; rover_safety/src/led_safety_node.cpp:233-239 | Needs the selected-input topic proposed in SWR-MUX-020. Stop conditions and latch semantics as in rover_twist_mux motion_lock_policy.cpp:39-54 and rover_arch/SAFETY_CHAIN.md:17-35.
SWR-SAF-020 | rover_safety | Gap | Proposed | SYS-SR-017, SYS-SR-010 | The rover_safety shall, in its platform mode manager, enter Low Battery when the battery state of charge falls below [TBD per SYS-SR-017] % and shall perform a safe stop (trip the software E-Stop) when it falls below [TBD per SYS-SR-017] %, with both thresholds as validated parameters. | rover_safety/src/domain/battery_safety_policy.cpp:34-59; rover_safety/config/led_safety.yaml:12-14 | Partially covered in hardware: the BMS level-one SOC-too-low alarm maps to DEAD in rover_battery and trips the E-Stop (SWR-SAF-002), but at a threshold configured in the BMS, not traceable in software. A NaN percentage (BMS watchdog) must not be read as 0 %.
SWR-SAF-021 | rover_safety | Gap | Proposed | SYS-SR-010, SYS-SR-022 | The rover_safety shall, in its platform mode manager, enter Fault when the battery verdict is not none, when a safety input is older than input_timeout (5.0 s), or when SafetyStatus.link_healthy is false, and shall leave Fault only when all these conditions have cleared. | rover_safety/src/safety_node.cpp:396-437; rover_safety/config/rover_safety.yaml:6 | Precedence between Emergency Stop, Fault and Low Battery to be defined with the state machine document.
SWR-SAF-022 | rover_safety | Deviation | Proposed | SYS-SR-009, SYS-SR-010 | The rover_safety shall, in rover_led_safety_node, display each SYS-SR-010 state with a dedicated rover_msgs/LedAnimation according to a documented state-to-LED mapping - at least Emergency Stop -> E_STOP (for hardware button, software button, motor-driver fault and held latch alike), Idle -> READY, Teleoperation -> MANUAL_ACTION, Autonomous -> AUTONOMOUS_READY/AUTONOMOUS_ACTION, Low Battery -> LOW_BATTERY, Fault -> ERROR - with colour and pattern per [TBD per SYS-SR-009]. | rover_safety/src/domain/led_animation_policy.cpp:29-35; rover_safety/src/led_safety_node.cpp:233-239; rover_msgs/msg/LedAnimation.msg:1-17 | Animation ids listed exist in rover_msgs/LedAnimation.msg; AUTONOMOUS_* are defined but unused today. The Boot state mapping is TBD (no existing animation). Colours/patterns are owned by rover_led.
SWR-TRN-005 | rover_transport | Partial | As-Built | SYS-SR-024 | The rover_transport shall, when a transport node's autostart parameter is true, trigger configure and then activate once from the executor immediately after construction, without retrying if configure fails. | rover_transport/rover_udp_driver/src/infrastructure/udp_receiver_node.cpp:77-88; rover_transport/rover_udp_driver/src/infrastructure/udp_sender_node.cpp:78-89; rover_battery/launch/rover_battery.launch.py:68; rover_led/launch/rover_led.launch.py:102; rover_crsf_teleop/launch/rover_crsf_teleop.launch.py:119 | Partial because a failed configure (UDP endpoint not yet available, PLC or BMS bridge not up) is never retried, so the node stays UNCONFIGURED until someone steps in. That conflicts with unattended start-up (SYS-SR-024). No test exercises the autostart path directly.
SWR-TRN-008 | rover_transport | Gap | Proposed | SYS-SR-005, SYS-SR-016, SYS-SR-022 | The rover_transport shall recover from a receive error on a UDP transport by re-arming the receive, and resume publishing without operator action. | rover_transport/rover_udp_driver/src/infrastructure/asio_udp_socket.cpp:171-175 | On a UDP receive error (other than operation_aborted) the handler logs and returns without re-arming. Recovery time is TBD because no SYS-SR sets it. The serial half of this requirement (reopening a UART) was dropped with rover_serial_driver.
SWR-TRN-019 | rover_transport | Partial | As-Built | SYS-SR-023 | The rover_transport shall abort a Modbus transaction whose reply does not arrive within ClientSettings.response_timeout_ms, which defaults to 500 ms and is configurable by the caller. | rover_transport/rover_modbus_driver/include/rover_modbus_driver/domain/client_settings.hpp:26; rover_transport/rover_modbus_driver/include/rover_modbus_driver/domain/client_settings.hpp:42; rover_transport/rover_modbus_driver/src/infrastructure/modbus_tcp_transport.cpp:22-27; rover_hardware_interface/src/rover_system/rover_a1_system.cpp:105-106 | Partial on two counts. First, no test exercises the response timeout (the e2e tests set 5000 ms only to avoid flakiness). Second, the rover URDF sets 150 ms (rover_description/urdf/rover_a1/rover_a1_macro.urdf.xacro:160), which is longer than the SYS-SR-023 100 ms budget. A single stalled transaction could therefore delay the E-stop state update past 100 ms; TBC by analysis. The hardware E-stop relay does not depend on this path.
SWR-TRN-020 | rover_transport | Gap | Proposed | SYS-SR-007, SYS-SR-023 | The rover_transport shall bound every Modbus TCP connection attempt, initial or re-dial, by a configurable connect timeout of [TBD per SYS-SR-023] ms, so that dialling a black-holed PLC host cannot block the caller for the kernel SYN-retry period. | rover_transport/rover_modbus_driver/include/rover_modbus_driver/application/modbus_discrete_io_client.hpp:44-50; rover_transport/rover_modbus_driver/src/infrastructure/modbus_tcp_transport.cpp:24 | The current mitigation is lazy re-dial with backoff (SWR-TRN-018), which limits dials to one per backoff window. The header argues the relay has already latched the E-stop when the link is down. The connect timeout value is TBD.
SWR-TRN-021 | rover_transport | Gap | Proposed | SYS-SR-022 | The rover_transport shall publish diagnostic status on /diagnostics at 1 Hz or faster for each UDP transport node (endpoint open/closed, bytes forwarded, bytes dropped while inactive, datagrams rejected by the source filter, last receive error) and for the Modbus link (connected/disconnected, current backoff), reporting ERROR when a transport has closed or the link is down. | rover_transport/rover_io_context/src/application/inbound_byte_bridge.cpp:45-48; rover_transport/rover_io_context/src/application/outbound_byte_bridge.cpp:46-54; rover_transport/rover_udp_driver/src/infrastructure/udp_receiver_node.cpp:110-149; rover_transport/rover_udp_driver/include/rover_udp_driver/infrastructure/asio_udp_socket.hpp:83; rover_transport/rover_modbus_driver/include/rover_modbus_driver/application/modbus_discrete_io_client.hpp:83-85 | No transport package depends on diagnostic_updater. The byte counters, rejectedDatagrams() and isConnected() already exist but nothing exposes them. Modbus link diagnostics could instead be published by the consumer (rover_hardware_interface); that choice is TBD. For the RC input, rover_crsf_teleop's 'RC UDP link' task already reports a silent datagram stream (SWR-CRSF-021).
SWR-MUX-019 | rover_twist_mux | Gap | Proposed | SYS-SR-007 | The rover_twist_mux shall publish motion_lock immediately when a received SafetyStatus or SafetyCommandEcho changes the evaluated lock state, in addition to the periodic publication, so that the lock path contributes to the 100 ms software E-Stop budget. | rover_twist_mux/src/infrastructure/motion_lock_node.cpp:120-123; rover_twist_mux/src/infrastructure/motion_lock_node.cpp:134-145; rover_arch/SAFETY_CHAIN.md:141 | The primary SYS-SR-007 path is the hardware interface write() gate and the PLC latch (SAFETY_CHAIN.md:199-202), so this is defence in depth; allocate the 100 ms budget across the chain before implementing.
SWR-MUX-020 | rover_twist_mux | Gap | Proposed | SYS-SR-010 | The rover_twist_mux shall publish which input is currently selected (or none, or locked) on a ROS topic whenever the selection changes, for use by the platform mode manager. | rover_twist_mux/launch/rover_twist_mux.launch.py:110-119 | Upstream twist_mux has no selected-input topic; this may need a small wrapper or a diagnostics-based adapter. Consumer: SWR-SAF mode manager (see rover_safety SWRS).

## Model Tests
Model test | Result | Known deviation | Verifies | Message
tCommandArbitration/testCommandWatchdog | FAIL (known deviation) | TRUE | SYS-SR-011, SWR-CTL-010, SWR-MUX-003 | deceleration starts later than 500 ms after the last command
tCommandArbitration/testPriorityOrder | PASS | FALSE | SYS-SR-005, SWR-MUX-002, SWR-MUX-003
tCommandArbitration/testSpeedLimitAllSources | PASS | FALSE | SYS-SR-004, SWR-CTL-008
tCommandArbitration/testAccelerationLimit | PASS | FALSE | SYS-SR-013, SWR-CTL-009
tCommandArbitration/testMotionLockMasksAllSources | PASS | FALSE | SWR-MUX-004, SWR-MUX-010, SYS-SR-006
tCommandArbitration/testStaleSafetyLocks | PASS | FALSE | SWR-MUX-008, SYS-SR-012
tCommandArbitration/testLockedAtStartup | PASS | FALSE | SWR-MUX-007
tEStopLatch/testSwEStopZeroCommandWorstCaseLink | FAIL (known deviation) | TRUE | SYS-SR-007, SWR-HWI-007 | worst-case SW E-stop to zero command = 240 ms
tEStopLatch/testEStopStatePublishLatency | FAIL (known deviation) | TRUE | SYS-SR-023, SWR-HWI-016 | worst-case E-stop state publish latency = 130 ms
tEStopLatch/testLatchResetRefusedWhileMoving | FAIL (known deviation) | TRUE | SWR-HWI-010 | latch reset accepted while moving
tEStopLatch/testStartupLatched | PASS | FALSE | SWR-HWI-011, SYS-SR-008
tEStopLatch/testHwButtonRemovesDrivePower | PASS | FALSE | SYS-SR-006
tEStopLatch/testLatchHoldsAfterButtonRelease | PASS | FALSE | SYS-SR-008, SWR-HWI-009
tEStopLatch/testSetDominantLatch | PASS | FALSE | SYS-SR-008
tEStopLatch/testSwEStopNeedsLatchReset | PASS | FALSE | SYS-SR-008, SWR-HWI-006, SWR-HWI-008
tEStopLatch/testSwResetRefusedWhileMoving | PASS | FALSE | SWR-HWI-008
tEStopLatch/testCpuWatchdogLossLatches | PASS | FALSE | SWR-HWI-012, SYS-SR-006
tEStopLatch/testSwEStopZeroCommandIdealLink | PASS | FALSE | SYS-SR-007, SWR-HWI-005, SWR-HWI-007
tPlatformModeManager/testLedDefinedForEveryState | FAIL (known deviation) | TRUE | SYS-SR-009, SWR-LED-020, SWR-MSG-010 | a state has no LED animation defined
tPlatformModeManager/testEveryStateReachable | PASS | FALSE | SYS-SR-010, SWR-SAF-018, SWR-SAF-019
tPlatformModeManager/testLedMapping | PASS | FALSE | SYS-SR-009, SWR-SAF-022, SWR-LED-010
tPlatformModeManager/testTeleopAutonomousFollowActiveSource | PASS | FALSE | SYS-SR-010, SWR-SAF-019, SWR-MUX-020
tPlatformModeManager/testEStopHasPriorityAndNeedsClear | PASS | FALSE | SYS-SR-008, SYS-SR-010, SWR-SAF-019
tPlatformModeManager/testFaultNeedsReset | PASS | FALSE | SWR-SAF-021, SYS-SR-010
tPlatformModeManager/testLowBatteryWarningAndSafeStop | PASS | FALSE | SYS-SR-017, SWR-SAF-020
tPlatformModeManager/testNoMotionOutsideOperationalStates | PASS | FALSE | SYS-SR-010, SWR-SAF-018
tSkidSteerKinematics/testEncoderFeedbackRate | FAIL (known deviation) | TRUE | SYS-SR-002 | Verification failed in tSkidSteerKinematics/testEncoderFeedbackRate. Framework Diagnostic: verifyGreaterThanOrEqual failed. Actual Value: 20 Minimum Value (Inclusive):
tSkidSteerKinematics/testImuPublishRate | FAIL (known deviation) | TRUE | SYS-SR-019, SWR-CTL-015 | Verification failed in tSkidSteerKinematics/testImuPublishRate. Framework Diagnostic: verifyGreaterThanOrEqual failed. Actual Value: 50 Minimum Value (Inclusive):
tSkidSteerKinematics/testStraightOdometryError | PASS | FALSE | SYS-SR-003, SWR-CTL-005, SWR-CTL-006
tSkidSteerKinematics/testRotationRoundTrip | PASS | FALSE | SYS-SR-003, SWR-CTL-005
tSkidSteerKinematics/testRimSpeedWithinJointLimit | PASS | FALSE | SYS-SR-004, SWR-CTL-011
tSkidSteerKinematics/testControlRates | PASS | FALSE | SYS-SR-002, SWR-CTL-001, SWR-CTL-016

## Verification Gaps
SWR (As-Built, verification by Test, no test exists) | Implementation | Requirement
SWR-BRG-001 | Implemented | The rover_bringup shall start the platform stack only when the environment variable ROBOT_HW_CONFIG_CORRECT is true (default true); otherwise it shall log INCORRECT_HW_CONFIG, start no platform node, and keep the launch process alive unless exit_on_wrong_hw is true.
SWR-DESC-007 | Implemented | The rover_description shall set the RoverA1System safety-link parameters modbus_host 192.168.88.11, modbus_port 502, modbus_connection_retry_count 0, modbus_connection_retry_delay_ms 1000, modbus_response_timeout_ms 150, safety_wdg_kick_period_ms 200, safety_io_poll_period_ms 100 and safety_latch_reset_pulse_ms 100.
SWR-DESC-011 | Implemented | The rover_description shall, in rover_load_urdf.launch.py, take the IMU, lidar and GPS mount poses from the ROVER_{IMU,LIDAR,GPS}_LOCALIZATION_{X,Y,Z} and _ORIENTATION_{R,P,Y} environment variables, falling back to the defaults (IMU xyz (-0.09, 0.0, 0.2), rpy (3.14159, 0.0, 0.0); lidar and GPS all 0.0) for unset or non-finite values.
SWR-DESC-013 | Implemented | The rover_description shall start robot_state_publisher as node rover_state_publisher_node in the requested namespace with the generated robot_description, frame_prefix "<namespace>/" and use_sim_time equal to use_sim, when publish_robot_state is true (default).
SWR-DIAG-010 | Implemented | The rover_diag_manager shall configure the diagnostic aggregator to publish diagnostics_agg at 1.0 Hz under the root path 'Rover'.
SWR-HWI-024 | Implemented | The rover_hardware_interface shall, in on_error(), assert the software E-Stop, broadcast an ERROR status on all diagnostic tasks and tear down the safety controller, drivers and ROS helper node.
SWR-LED-008 | Implemented | The rover_led shall publish each panel frame additionally on led/channel_<n>_preview (sensor_msgs/Image, best effort, depth 1) at preview_publish_rate, default 5.0 Hz, and shall create no preview topics when preview_publish_rate is 0.
SWR-LED-018 | Implemented | The rover_led driver shall publish on diagnostics, hardware id 'Bumper Led', a 'Led driver status' that is ERROR 'Driver is not active!' when not Active, WARN 'Driver is not yet functional!' while LED control is pending, ERROR when obtaining control failed, and OK 'Driver is fully functional.' when control is granted, including the lifecycle state and LED control status.
SWR-LOC-002 | Implemented | The rover_localization shall configure rover_ekf_node to run at 50.0 Hz in 2D mode (two_d_mode true) with a sensor timeout of 0.1 s.
SWR-MSG-012 | Implemented | The rover_msgs shall generate all messages and services with rosidl_generate_interfaces depending only on builtin_interfaces, geometry_msgs and std_msgs, and export rosidl_default_runtime.
SWR-TRN-005 | Partial | The rover_transport shall, when a transport node's autostart parameter is true, trigger configure and then activate once from the executor immediately after construction, without retrying if configure fails.
SWR-TRN-007 | Implemented | The rover_transport shall keep the UDP receiver armed after a successful zero-length datagram, so that later datagrams are still published.
SWR-TRN-019 | Partial | The rover_transport shall abort a Modbus transaction whose reply does not arrive within ClientSettings.response_timeout_ms, which defaults to 500 ms and is configurable by the caller.

## Open Questions
Ref | Question | Answer | Answered By
SYS-SR-004 | The Open Questions answer for the angular limit reads '1.7 m/s2'. Is it 1.7 rad/s (as the requirement text says)?
SYS-SR-005 | The code fixes the 4 sources and their order: ELRS RC (110) > Foxglove joystick (100) > Driver UI (8) > Nav 2 (5). Confirm and write them into SYS-SR-005.
SYS-SR-007 | write() only sees the SW E-stop after the 10 Hz PLC poll reads it back (model: up to 90 ms ideal, 240 ms worst case). Change the design (set the E-stop locally at the service call, faster poll) or relax 100 ms?
SYS-SR-011 | The as-built watchdog starts decelerating up to 520 ms after the last command (0.5 s timeout checked at 50 Hz). Lower cmd_vel_timeout to 0.48 s, or accept 520 ms?
SYS-SR-019 | imu/data is published at 50 Hz (the sensor samples at 125 Hz). Raise rover_imu_broadcaster to 100 Hz (it divides the 100 Hz controller_manager rate)?
SYS-SR-023 | The E-stop state reaches safety_status through a 10 Hz poll and a 20 Hz publisher (up to 130 ms in the model). Poll faster and publish on change, or relax 100 ms?
SYS-SR-010 | Approve the proposed PlatformModeManager (behaviour/PlatformModeManager.slx): states, transitions, priorities (E-stop > Fault > Low Battery) and the owner (rover_safety).
SYS-SR-009 | Approve the proposed state-to-LED mapping (Idle READY, Teleoperation MANUAL_ACTION, Autonomous AUTONOMOUS_ACTION, E-stop E_STOP, Fault ERROR, Low Battery LOW_BATTERY / CRITICAL_BATTERY) and define a Boot animation.
SYS-SR-017 | Set the Low Battery and safe-stop SOC thresholds. The model uses the LED thresholds 40 % / 10 % as an ASSUMPTION.
SYS-SR-012 | Set the operator-link timeout. Must loss of the web (Wi-Fi) link stop the rover, as the RC link loss does?
SYS-SR-001 | The URDF now matches the CAD (57.27 kg, 2026-10-07). The xlsx Mass Properties sheet (54.35 kg, CoM height 0.270 m, 2026-09-25) predates it. Re-take the sheet from the current CAD?
SYS-SR-020 | Write 'ROS 2 Lyrical, rmw_zenoh_cpp' into SYS-SR-020 to replace [TBD distribution].
SWR-HWI-010 | rover_arch/SAFETY_CHAIN.md section 5 says the zero-velocity reset invariant covers the latch, but resetEStopLatch() does not check it. Fix the code or the document?